## Stories
Sprint | Who | Story | Estimate
1 |  | 2013-04-11
|  | Story #1 | 1
|  | Story #2 | 3
|  | Story #3 | 5
2 |  | 2013-04-25 |  | 9
|  | Story #4 | 5
|  | Story #5 | 3
|  | Story #6 | 5
3 |  | 2013-05-09 |  | 13
|  | Story #7 | 3
|  | Story #8 | 3
|  | Story #9 | 5
4 |  | 2013-05-23 |  | 11
|  | Story #10 | 3
|  | Story #11 | 3
|  | Story #12 | 5
5 |  | 2013-06-06 |  | 11
|  | Story #13 | 1
|  | Story #14 | 3
|  | Story #15 | 5
Release June 1
|  | Total | 53
|  | Completed | 44
|  | Remaining | 9
|  | % Complete | 83.02%
|  | Avg Velocity | 11
|  | Estimated # Iterations Remaining | 0.81818
Parking Lot
Stuff we didn't need #1
Stuff we didn't need #2
Dropped
Nice to have story #1
Nice to have story #2

## Sprint Data
| 2013-04-11 | 2013-04-25 | 2013-05-09 | 2013-05-23
| 1 | 2 | 3 | 4
Total Effort | 53 | 53 | 53 | 53
Velocity | 9 | 13 | 11 | 11
Remaining | 44 | 31 | 20 | 9
Completed | 9 | 22 | 33 | 44
% complete | 16.98% | 41.51% | 62.26% | 83.02%